## Collaborative Visualization for
Task Name | Duration | Start | Finish | Days | % Time Spent out of 260 Days | Predecessors | Assigned To | % Complete | Status | Comments | Column11
Phase 1: Planning | 46d | 2020-08-28 | 2020-10-30 | 64 | 24.6154 |  |  | 95% | In Progress | Oct 19 is the day we reach 20% of our time.
Establish Communications | 6d | 2020-08-28 | 2020-09-04 |  |  |  |  | 100% | Complete | Discord, Zoom
Establish Centralized File Share | 6d | 2020-08-28 | 2020-09-04 |  |  |  |  | 100% | Complete | Onedrive/Sharepoint
Establish Team Roles | 6d | 2020-08-28 | 2020-09-04 |  |  |  |  | 100% | Complete
Establish Meeting Times w/ Liasions and Team | 6d | 2020-08-28 | 2020-09-04 |  |  |  |  | 100% | Complete | 8:30 AM for students, 9:30 AM for Liasions and Advisor
Create Meeting Agenda Templates | 6d | 2020-08-28 | 2020-09-04 |  |  |  |  | 100% | Complete
Resource Allocation | 26d | 2020-09-25 | 2020-10-30 |  |  |  |  | 90% | In Progress | Split the team into 2 groups. Group 1 focuses on VR while Group 2 focuses on Web
Capacity Planning | 26d | 2020-09-25 | 2020-10-30 |  |  |  |  | 90% | Not Started
Feasibility Assessment | 26d | 2020-09-25 | 2020-10-30 |  |  |  |  | 100% | In Progress | Need to make a decision by next week, so we can start on stuff.
VR Room and Unity | 26d | 2020-09-25 | 2020-10-30 |  |  |  |  | 100% | In Progress
WebVR and JS | 26d | 2020-09-25 | 2020-10-30 |  |  |  |  | 100% | In Progress | Node.js, Socket.io showing great promise with Cesium usage.
Project Scheduling | 17d | 2020-10-08 | 2020-10-30 |  |  |  | Stanley | 100% | In Progress
Project Plan | 17d | 2020-10-08 | 2020-10-30 |  |  |  | Stanley | 90% | In Progress
Phase 2: Requirements | 35d | 2020-10-26 | 2020-12-11 | 47 | 18.0769 |  |  | 1% | In Progress
Create Standardized Documentation | 21d | 2020-10-26 | 2020-11-23 | [5 empty] | Not Started | Chris
Consolidate Existing Requirements Documentation | 21d | 2020-10-26 | 2020-11-23 | [5 empty] | Not Started | Chris
Personas Document | 21d | 2020-10-26 | 2020-11-23 | [5 empty] | Not Started | Chris
Scenarios Document | 21d | 2020-10-26 | 2020-11-23 | [5 empty] | Not Started | Will do Scenarios when we have something slightly developed/in mind?
Prototypes Document | 21d | 2020-10-26 | 2020-11-23 | [5 empty] | Not Started | Will do Prototypes when we have something slightly developed/in mind?
Software Requirements Specification (SRS) | 35d | 2020-10-26 | 2020-12-11 |  |  |  |  | 2% | Not Started | Don't know due date yet
Introduction | 35d | 2020-10-26 | 2020-12-11 |  |  |  |  | 16% | Not Started | Miguel
Purpose | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started | Miguel
Intended Audience and Reading Suggestions | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started | Miguel
Product Scope | 35d | 2020-10-26 | 2020-12-11 |  |  |  |  | 80% | Started | Stanley
Definitions, Acronyms, and Abbreviations | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started | Miguel
References | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started | Miguel
Overall Description | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
System Analysis | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Product Perspective | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Product Functions | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
User Classes and Characteristics | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Operating Environment | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Design and Implementaiton Constraints | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
User Documentation | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Assumptions and Dependencies | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Apportioning of Requirements | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
External Interface Requirements | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
User Interfaces | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Hardware Interfaces | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Software Interfaces | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Communications Interfaces | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Requirements Specification | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Functional Requirements | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
External Interface Requirements | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Logical Database Requirements | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Design Constraints | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Other Nonfunctional Requirements | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Performance Requirements | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Safety Requirements | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Security Requirements | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Software Quality Attributes | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Business Rules | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Other Requirements | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Appendix | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
A | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
B | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
C | 35d | 2020-10-26 | 2020-12-11 | [5 empty] | Not Started
Phase 3: Design | 28d | 2020-12-11 | 2021-01-19 | 40 | 15.3846 |  |  |  | Not Started
Software Architecture | 12d | 2020-12-11 | 2020-12-28 | 18
UI Storyboard | 12d | 2020-12-11 | 2020-12-28 | 18
UI Mockup | 12d | 2020-12-11 | 2020-12-28 | 18
Frontend Infrastructure | 12d | 2020-12-11 | 2020-12-28 | 18
Backend Infrastructure | 12d | 2020-12-11 | 2020-12-28 | 18
Database Design | 12d | 2020-12-11 | 2020-12-28 | 18
Server Resources/Locations | 12d | 2020-12-11 | 2020-12-28 | 18
Software Design Document (SDD) | 28d | 2020-12-11 | 2021-01-19 | 40 |  |  |  |  | Not Started | Don't know due date yet
Introduction | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
Purpose | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
Document Conventions | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
Intended Audience and Reading Suggestions | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
System Overview | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
Design Considerations | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
Assumptions and dependencies | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
General Constraints | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
Goals and Guidelines | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
Development Methods | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
Architectural Strategies | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
System Architecture | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
Policies and Tactics | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
Choice of Which Specific Products Used | 28d | 2020-12-11 | 2021-01-19
Plans for ensuring requirements traceability | 28d | 2020-12-11 | 2021-01-19
Plans for testing the software | 28d | 2020-12-11 | 2021-01-19
Detailed System Design | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
Detailed Lower Level Component Design | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
User Interface | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
Database Design | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
Requirements Validation and Verification | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
Glossary | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
References | 28d | 2020-12-11 | 2021-01-19 | [5 empty] | Not Started
Phase 4: Implementation | 39d | 2021-01-05 | 2021-02-26 | 53 | 20.3846 |  |  |  | Not Started
Phase 5: Testing | 46d | 2021-02-26 | 2021-04-30 | 64 | 24.6154 |  |  |  | Not Started
Phase 6: Closure | 11d | 2021-05-01 | 2021-05-14 | 14 | 5.3846 |  |  |  | Not Started

## Comments
Row 4 | Project Lead Montague La France Project Co-Lead Stanley Do Architecture/Design Lead Abdullah Alshebly Customer Liaison/Requirements Lead Christopher Smallwood Component Lead Jose Garcia Component Lead Johnny Lee Component Lead Odasys Soberanes QA Lead David Tang Documentation Lead Zipeng Guo Demo/Presentation Lead Miguel Sanchez | Stanley Do | 10/08/20 7:57 PM
Row 9 | We want to make a decision to choose which path we would like to take (Unity development or web development path) | Stanley Do | 10/25/20 10:38 PM
Row 20 | Do not know the exact due date for deliverable | Stanley Do | 10/25/20 10:27 PM
Row 25 | Also would benefit from being added to throughout the project | Stanley Do | 11/05/20 7:58 PM
Row 26 | This is more of a team thing | Stanley Do | 11/05/20 7:58 PM
Row 58 | Do not know the exact due date for deliverable. | Stanley Do | 10/25/20 10:27 PM
Row 90 | Will be determined after design phase | Stanley Do | 12/10/20 10:22 PM